## Weekly Gantt Chart Template
GANTT CHART
| PROJECT: |  | Railway Reservation System
[5 empty] | 15/02/2023 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Task name | Start date | End date | Duration | Assigned | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16
Requirements | 15/02/2023 | 25/02/2023 | 10 Days | Team MWM
Project planning | 15/02/2023 | 17/02/2023 | 3 d | Wahaj
Project Scheduling | 18/02/2023 | 21/02/2023 | 3d | Muneeb
Resource Management | 22/02/2023 | 25/02/2023 | 4d | Muneeb
System Analysis and Design | 26/02/2023 | 2023-05-03 | 8 Dayds | Team MWM
Use Case Daigrams | 26/02/2023 | 27/02/2023 | 2d | Wahaj
Class Daigrams | 28/3/2023 | 1900-01-02 | 2d | Muteeb
Sequence Daigrams | 2023-02-03 | 2023-03-03 | 2d | Munneb
Database Design | 2023-04-03 | 2023-05-03 | 2d | Wahaj
Developement | 2023-06-03 | 26/03/2023 | 20 Days | Team MWM
Develope Admin Module | 2023-06-03 | 13/03/2023 | 7 d | Wahaj,Muneeb
Develope Passenger Module | 14/3/2023 | 20/3/2023 | 7d | Muteeb
Integerated Systems Module | 21/3/2023 | 23/3/2023 | 4d | Wahaj
Development Finished | 24/03/2023 | 26/03/2023 | 3d | Muneeb
Testing and Quality Assurance | 27/03/2023 | 2023-06-04 | 10 Days | Team MWM
Perform Testing System | 27/03/2023 | 29/03/2023 | 3d | Wahaj,Muteeb
Correct issues found | 29/03/2023 | 31/03/2023 | 3d | Muneeb
System Delivery | 2023-01-04 | 2023-03-04 | 2d | Muteeb,Muneeb
User Accepting Test | 2023-04-04 | 2023-06-04 | 2d | Wahaj
Documentation | 2023-07-04 | 14/4/2023 | 7 Days | Team MWM
User Manual | 2023-07-04 | 2023-10-04 | 3d | Wahaj
Technical Documentation | 2023-11-04 | 14/4/2023 | 4d | Muneeb
Deployement | 15/4/2023 | 21/4/2023 | 7 Days | Team MWM
System installation | 15/4/2023 | 18/4/2023 | 4d | Wahaj,Muneeb
Maintenance | 19/4/2023 | 21/4/2023 | 3d | Muteeb

## Useful Tips
USEFUL TIPS
1 | When enteringactivity start and end dates in columns "D" and "E" use the following date format: DD/MM/YYYY
2 | To change colour of fill and text in cells, use HOME -> FONT tool palette.
3 | To change LOGO image, right click on it and choose CHANGE PICTURE.

## ©
© TemplateLab.com